## Risk Register
Risk ID | Asset | Threat | Vulnerability | Risk Description | Risk Category | ISO 27001 mapping | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Existing Controls | Control Effectiveness (1-5) | Residual Risk Score | Risk Level | Risk Owner | Treatment Strategy | Treatment Strategy | Review Date | Status
R1 | Authentication System | External attacker | No MFA / weak lockout thresholds | Repeated failed login attempts could enable unauthorized account access through brute-force credential attacks. | Cybersecurity | A.5.17 Authentication information, A.8.5 Secure authentication, A.5.15 Access control | 4 | 4 | 16 | Repeated failed login attempts could enable unauthorized account access through brute-force credential attacks. | 2 | 14 | Medium | IT Security | Mitigate | Implement multi-factor authentication (MFA) for all external and privileged users and enforce automated account lockout after repeated failed login attempts. | 2026-02-17 | Open
R2 | Admin Accounts | Admin Accounts | High-value accounts lack additional protections | Targeted attacks against administrative accounts could result in full system compromise if credentials are breached. | Cybersecurity | A.5.16 Identity management, A.8.2 Privileged access rights, A.5.18 Access rights, A.5.15 Access control | 3 | 5 | 15 | Role-based access controls, limited admin account usage, logging of privileged activity. | 2 | 13 | Medium | IT Security | Mitigate | Enforce privileged access management (PAM), conduct quarterly access reviews, and require strong authentication for all administrative accounts. | 2026-02-17 | Open
R3 | Login infrastructure | Automated attack attempts | No rate limiting or IP blocking | Absence of login rate-limiting controls allows automated attack attempts to continue without restriction. | Cybersecurity | A.8.20 Network security, A.8.16 Monitoring activities, A.8.5 Secure authentication, A.8.8 Management of technical vulnerabilities | 4 | 3 | 12 | Basic authentication logging, manual monitoring. | 1 | 11 | Medium | IT Security | Mitigate | Deploy application-level rate limiting, IP reputation filtering, and automated blocking of repeated failed authentication attempts. | 2026-02-17 | Open
R4 | Logging & Monitoring System | Delayed detection | Limited alert rules | Limited SIEM alert rules may delay detection of repeated authentication attacks and suspicious activity. | Cybersecurity | A.8.15 Logging, A.8.16 Monitoring activities, A.5.25 Assessment and decision on information security events, A.5.26 Response to information security incidents | 3 | 4 | 12 | Centralized log collection, manual review processes | 2 | 10 | Medium | IT Security | Mitigate | Configure real-time SIEM correlation rules for abnormal authentication activity and establish automated high-severity SOC alerts. | 2026-02-17 | Open
R5 | Authentication System | Credential reuse | Absence of MFA | Stolen credentials may be reused to access systems without additional verification. | Cybersecurity | A.5.15 Access control, A.5.16 Identity management, A.5.17 Authentication information, A.8.5 Secure authentication | 4 | 4 | 16 | Password policy, account lockout thresholds | 2 | 14 | Medium | IT Security | Mitigate | Implement MFA across all user access points. | 2026-02-17 | Open
R6 | Identity & Access Management | Privilege misuse | Excessive permissions | Over-privileged accounts increase damage potential if compromised. | Cybersecurity | A.8.2 Privileged access rights, A.5.18 Access rights, A.5.15 Access control, A.5.3 Segregation of duties | 3 | 5 | 15 | Manual approvals | 2 | 13 | Medium | IT Security | Mitigate | Enforce least-privilege access and conduct quarterly access reviews. | 2026-02-17 | Open
R7 | SIEM Platform | Undetected attacks | No automated alerting | Ongoing brute-force attacks may persist without timely detection. | Cybersecurity | A.8.15 Logging, A.8.16 Monitoring activities, A.5.25 Assessment and decision on information security events, A.5.26 Response to information security incidents | 4 | 4 | 16 | Manual Review | 1 | 15 | High | IT Security | Mitigate | Implement real-time correlation rules and SOC alerts. | 2026-02-17 | Open
R8 | Incident Response Process | Delayed containment | Lack of documented playbooks | Inconsistent response may delay breach containment. | Operational | A.5.24 Information security incident management planning and preparation, A.5.26 Response to information security incidents, A.5.27 Learning from information security incidents | 3 | 4 | 12 | Analysis Judgement | 2 | 10 | Medium | Operations Lead | Mitigate | Develop and document incident response playbooks. | 2026-02-17 | Open
R9 | Log Management System | Evidence loss | Short retention period | Historical attack data may be unavailable for investigations. | Cybersecurity | A.8.15 Logging, A.5.33 Protection of records, A.8.13 Information backup | 3 | 4 | 12 | Limited SIEM storage | 2 | 10 | Medium | IT Security | Mitigate | Extend log retention and backup policies. | 2026-02-17 | Open
R10 | Risk Management Program | Emerging risks unmanaged | Lack of periodic risk review | Failure to regularly review risks may result in delayed identification of new security threats and outdated controls. | Regulatory, Operational | A.5.4 Management responsibilities, A.5.9 Inventory of information and other associated assets, "A.5.36 Compliance with policies, rules and standards for information security", A.5.1 Policies for information security | 2 | 3 | 6 | Initial risk assessment, Informal management check-ins | 2 | 4 | Low | Risk Officer | Mitigate | Establish formal quarterly risk review cycles and document management approvals. | 2026-02-17 | Open
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low
[9 empty] | 0 |  |  | 0 | Low

## ISO_Controls
A.5.1 Policies for information security
A.5.2 Information security roles and responsibilities
A.5.3 Segregation of duties
A.5.4 Management responsibilities
A.5.5 Contact with authorities
A.5.6 Contact with special interest groups
A.5.7 Threat intelligence
A.5.8 Information security in project management
A.5.9 Inventory of information and other associated assets
A.5.10 Acceptable use of information and assets
A.5.11 Return of assets
A.5.12 Classification of information
A.5.13 Labelling of information
A.5.14 Information transfer
A.5.15 Access control
A.5.16 Identity management
A.5.17 Authentication information
A.5.18 Access rights
A.5.19 Information security in supplier relationships
A.5.20 Addressing information security within supplier agreements
A.5.21 Managing information security in the ICT supply chain
A.5.22 Monitoring, review and change management of supplier services
A.5.23 Information security for use of cloud services
A.5.24 Information security incident management planning and preparation
A.5.25 Assessment and decision on information security events
A.5.26 Response to information security incidents
A.5.27 Learning from information security incidents
A.5.28 Collection of evidence
A.5.29 Information security during disruption
A.5.30 ICT readiness for business continuity
A.5.31 Legal, statutory, regulatory and contractual requirements
A.5.32 Intellectual property rights
A.5.33 Protection of records
A.5.34 Privacy and protection of personally identifiable information (PII)
A.5.35 Independent review of information security
A.5.36 Compliance with policies, rules and standards for information security
A.5.37 Documented operating procedures
A.6.1 Screening
A.6.2 Terms and conditions of employment
A.6.3 Information security awareness, education and training
A.6.4 Disciplinary process
A.6.5 Responsibilities after termination or change of employment
A.6.6 Confidentiality or non-disclosure agreements
A.6.7 Remote working
A.6.8 Information security event reporting
A.7.1 Physical security perimeters
A.7.2 Physical entry controls
A.7.3 Securing offices, rooms and facilities
A.7.4 Physical security monitoring
A.7.5 Protecting against physical and environmental threats
A.7.6 Working in secure areas
A.7.7 Clear desk and clear screen
A.7.8 Equipment siting and protection
A.7.9 Security of assets off-premises
A.7.10 Storage media
A.7.11 Supporting utilities
A.7.12 Cabling security
A.7.13 Equipment maintenance
A.7.14 Secure disposal or reuse of equipment
A.8.1 User endpoint devices
A.8.2 Privileged access rights
A.8.3 Information access restriction
A.8.4 Access to source code
A.8.5 Secure authentication
A.8.6 Capacity management
A.8.7 Protection against malware
A.8.8 Management of technical vulnerabilities
A.8.9 Configuration management
A.8.10 Information deletion
A.8.11 Data masking
A.8.12 Data leakage prevention
A.8.13 Information backup
A.8.14 Redundancy of information processing facilities
A.8.15 Logging
A.8.16 Monitoring activities
A.8.17 Clock synchronization
A.8.18 Use of privileged utility programs
A.8.19 Installation of software on operational systems
A.8.20 Network security
A.8.21 Security of network services
A.8.22 Segregation of networks
A.8.23 Web filtering
A.8.24 Use of cryptography
A.8.25 Secure development life cycle
A.8.26 Application security requirements
A.8.27 Secure system architecture and engineering principles
A.8.28 Secure coding
A.8.29 Security testing in development and acceptance
A.8.30 Outsourced development
A.8.31 Separation of development, test and production environments
A.8.32 Change management
A.8.33 Test information
A.8.34 Protection of information systems during audit testing